## Info
QAcart Todo Application
Project Name		Todo Application
Tester Name		Rehab Essam Hassan Mahmoud
Software Version		V 1.0
Browsers		Chrome Version 141.0.7390.123 (Official Build) (64-bit). / Microsoft Edge Version 142.0.3595.69 (Official build) (64-bit). / Mozilla Firefox Version144.0.2 (Official build) ‏(64-bit).
Date		13/11/2025

## SignUp
Defect Report					Defect Report					Defect Report					Defect Report					Defect Report					Defect Report					Defect Report

Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0
Bug ID	SU_B001					Bug ID	SU_B002					Bug ID	SU_B003					Bug ID	SU_B004					Bug ID	SU_B005					Bug ID	SU_B006					Bug ID	SU_B007
Related TC	SU_TC014					Related TC	SU_TC015					Related TC	SU_TC016					Related TC	SU_TC017					Related TC	SU_TC023					Related TC	SU_TC025					Related TC	SU_TC026
Title	Signup should not be possible if the password does not contain uppercase letter (invalid)					Title	Signup should not be possible if the password does not contain lowercase letter (invalid)					Title	Signup should not be possible if the password does not contain at least one number (invalid)					Title	Signup should not be possible if the password does not contain a special characters (invalid)					Title	Signup should be possible if all the data is valid, and press the enter button on the keyboard instead of clicking on the signup button using the mouse					Title	Signup page should be compatible with different screen sizes by using different environments.					Title	The signup page should be compatible with different screen display modes in various environments.
Description	User can signup when he/she enters a password that doesn't contain an uppercase letter. This happens in all browsers with different versions and screen sizes.					Description	User can signup when he/she enters a password that doesn't contain an lowercase letter. This happens in all browsers with different versions and screen sizes.					Description	User can signup when he/she enters a password that doesn't contain any numbers. This happens in all browsers with different versions and screen sizes.					Description	User can signup when he/she enters a password that doesn't contain any special characters. This happens in all browsers with different versions and screen sizes.					Description	User can't signup when using "Enter" button instead of clicking signup button using the mouse. This happens in all browsers with different versions and screen sizes.					Description	The signup page doesn't adapt to different screen sizes of mobiles. / This happens on all mobile devices, including iPhones and Samsungs.					Description	The signup page doesn't adapt with different screen displaying modes of mobiles. / This happens in all mobiles including iphone and samsung.
Steps	1- Fill a correct first Name. / 2- Fill a correct last name. / 3- Fill a correct email format, and the email should not be registed in the database. / 4- Fill the password without uppercase letter. / 5- Fill a correct confirm password. / 6- Click on signup button.					Steps	1- Fill a correct first Name. / 2- Fill a correct last name. / 3- Fill a correct email format, and the email should not be registed in the database. / 4- Fill the password without lowercase letter. / 5- Fill a correct confirm password. / 6- Click on signup button.					Steps	1- Fill a correct first Name. / 2- Fill a correct last name. / 3- Fill a correct email format, and the email should not be registed in the database. / 4- Fill the password without any numbers. / 5- Fill a correct confirm password. / 6- Click on signup button.					Steps	1- Fill a correct first Name. / 2- Fill a correct last name. / 3- Fill a correct email format, and the email should not be registed in the database. / 4- Fill the password without any special characters. / 5- Fill a correct confirm password. / 6- Click on signup button.					Steps	1- Fill a correct first name. / 2- Fill a correct second name. / 3- Fill a correct email format, and the email should not be registed in the database. / 4- Fill a correct password. / 5- Fill a correct confirm password. / 6- Press "Enter" button.					Steps	1-Open developer tools. / 2-Change screen dimensions by choosing different environments.					Steps	1-Open developer tools. / 2-Select rotation mode.
Test Data	1- First name : Rehab / 2- Last name : Al-Ashry / 3- Email : test34@gmail.com / 4- Password : rehab47! / 5- Confirm Password : rehab47!					Test Data	1- First name : Rehab / 2- Last name : Al-Ashry / 3- Email : test35@gmail.com / 4- Password : REHAB47! / 5- Confirm Password : REHAB47!					Test Data	1- First name : Rehab / 2- Last name : Al-Ashry / 3- Email : test36@gmail.com / 4- Password : RehabAl! / 5- Confirm Password : RehabAl!					Test Data	1- First name : Rehab / 2- Last name : Al-Ashry / 3- Email : test37@gmail.com / 4- Password : RehabAlashry74 / 5- Confirm Password : RehabAlashry74					Test Data	1- First name : Rehab / 2- Last name : Al-Ashry / 3- Email : test43@gmail.com / 4- Password : Rehab74! / 5- Confirm Password : Rehab74!					Test Data	Try using different environments as mobiles and ipad, by changing dimensions using developer tools.					Test Data	Try using different screen displaying mode by clicking rotate icon.
Expected Results	Should show this error "Password must be Minimum eight characters, at least one uppercase letter, one lowercase letter, one number and one special character"					Expected Results	Should show this error "Password must be Minimum eight characters, at least one uppercase letter, one lowercase letter, one number and one special character"					Expected Results	Should show this error "Password must be Minimum eight characters, at least one uppercase letter, one lowercase letter, one number and one special character"					Expected Results	Should show this error "Password must be Minimum eight characters, at least one uppercase letter, one lowercase letter, one number and one special character"					Expected Results	Should signup the user correctly					Expected Results	Signup page should be compatible and runs correctly on various systems with various screen sizes without any need to be modified.					Expected Results	Signup page should be compatible and runs correctly on various systems with various screen displaying modes without any need to be modified.
Actual Result	Signup was correct					Actual Result	Signup was correct					Actual Result	Signup was correct					Actual Result	Signup was correct					Actual Result	Signup can't be done					Actual Result	The signup page isn't compatible and needs modifications because it doesn't adapt to different screen sizes; it appears on the left side of the page instead of being centered.					Actual Result	The signup page isn't compatible and needs modifications as its appearance differs and doesn't adapt to different screen display modes.
Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit)					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit)					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit)					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit)					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit)					Environment	iphone SE - iphone XR - iphone 12 Pro - iphone 14 Pro Max - Pixel 7 - Samsung Galaxy S8+ - Samsung Galaxy S20 ultra - Galaxy Z fold 5					Environment	iphone SE - iphone XR - iphone 12 Pro - iphone 14 Pro Max - Pixel 7 - Samsung Galaxy S8+ - Samsung Galaxy S20 ultra - Galaxy Z fold 5
Screenshot / Video					Screenshot / Video					Screenshot / Video					Screenshot / Video					Screenshot / Video					Screenshot / Video	https://drive.google.com/file/d/1cDg6_2fszmrPcnebwPcaP6a8G78Mr5lt/view?usp=sharing					Screenshot / Video	https://drive.google.com/file/d/1o-dcQa4DY7EqJwq6y8U9CzVEev8zinD6/view?usp=sharing
Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5
Priority	Meduim					Priority	Meduim					Priority	Meduim					Priority	Meduim					Priority	Low					Priority	High					Priority	High
Status	Opend					Status	Opend					Status	Opend					Status	Opend					Status	Opend					Status	Opend					Status	Opend
© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025

## Login
Defect Report					Defect Report					Defect Report					Defect Report

Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0
Bug ID	LI_B001					Bug ID	LI_B002					Bug ID	LI_B003					Bug ID	LI_B004
Related TC	LI_TC007					Related TC	LI_TC009					Related TC	LI_TC010					Related TC	LI_TC006
Title	Login should be possible if all the data is valid, and press the enter button on the keyboard instead of clicking on the login button using the mouse					Title	login page should be compatible with different screen sizes by using different environments.					Title	The login page should be compatible with different screen display modes in various environments.					Title	The "Forgotten password" link on login page should appear after 3 wrong trials.
Description	User can't login when using "Enter" button instead of clicking login button using the mouse. This happens in all browsers / with different versions and screen sizes.					Description	The login page doesn't adapt to different screen sizes of mobiles. / This happens on all mobile devices, including iPhones and Samsungs.					Description	The login page doesn't adapt with different screen displaying modes of mobiles. / This happens in all mobiles including iphone and samsung.					Description	User can't find the "Forgotten password" link when entering wrong password 3 times or even more.
Steps	1- Fill a correct email format, and the email should be registered in the database. / 2- Fill a correct password / 3- Press "Enter" button					Steps	1-Open developer tools. / 2-Change screen dimensions by choosing different environments.					Steps	1-Open developer tools. / 2-Select rotation mode.					Steps	1- Fill a correct email format, and the email should be registered in the database. / 2- Fill a wrong password / 3- Click "login" button / 4-Repeat these steps 3 times.
Test Data	1- Email : test38@gmail.com / 2- Password : Rehab74!					Test Data	Try using different environments as mobiles and ipad, by changing dimensions using developer tools.					Test Data	Try using different screen displaying mode by clicking rotate icon.					Test Data	1- Email : test38@gmail.com / 2- Password : 1234567
Expected Results	Should log in the user correctly					Expected Results	login page should be compatible and runs correctly on various systems with various screen sizes without any need to be modified.					Expected Results	login page should be compatible and runs correctly on various systems with various screen displaying modes without any need to be modified.					Expected Results	1-The link is readable and correctly labeled. / 2-The link is clickable. / 3-Clicking the link redirects the user to the "Find Your Account" page, where the user enters their email address to receive a code to reset their password.
Actual Result	login can't be done					Actual Result	The login page isn't compatible and needs modifications because it doesn't adapt to different screen sizes; it appears on the left side of the page instead of being centered.					Actual Result	The login page isn't compatible and needs modifications as its appearance differs and doesn't adapt to different screen display modes.					Actual Result	The link did not appear
Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit)					Environment	iphone SE - iphone XR - iphone 12 Pro - iphone 14 Pro Max - Pixel 7 - Samsung Galaxy S8+ - Samsung Galaxy S20 ultra - Galaxy Z fold 5					Environment	iphone SE - iphone XR - iphone 12 Pro - iphone 14 Pro Max - Pixel 7 - Samsung Galaxy S8+ - Samsung Galaxy S20 ultra - Galaxy Z fold 5					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit)
Screenshot / Video					Screenshot / Video	https://drive.google.com/file/d/1c4VlQ31se8oNXEPsli1qCBM7F2TVzu0a/view?usp=sharing					Screenshot / Video	https://drive.google.com/file/d/1kwMxKKRb46aNZIOW3PT3lap_nw0u9VJf/view?usp=sharing					Screenshot / Video	https://drive.google.com/file/d/1gI2wmMQmozSpUctBoBqH01qs6l2MwKDL/view?usp=sharing
Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5
Priority	Low					Priority	High					Priority	High					Priority	High
Status	Opend					Status	Opend					Status	Opend					Status	Opend
© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025

## Todo_Page
Defect Report					Defect Report					Defect Report					Defect Report					Defect Report					Defect Report					Defect Report					Defect Report

Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0					Release	V.1.0
Bug ID	TP_B001					Bug ID	TP_B002					Bug ID	TP_B003					Bug ID	TP_B004					Bug ID	TP_B005					Bug ID	TP_B006					Bug ID	TP_B007					Bug ID	TP_B008
Related TC	TP_TC003					Related TC	TP_TC012					Related TC	TP_TC016					Related TC	TP_TC023					Related TC	TP_TC024					Related TC	TP_TC025					Related TC	TP_TC026					Related TC	TP_TC027
Title	User name should be displayed as user when it is assigned with just 2 characters.					Title	The Welcome Message should be readable and accepted by the User.					Title	Adding a new todo consists of 3 characters shouldn't be accepted.					Title	User should be redirected to a todo list consists of 5 todos after deleting the 6th todo.					Title	After reloading the website, the pagination state (current page) should remain consistent.					Title	The todo list and the todo page should be scalable with pagination when adding a huge number of todos, which leads to multiple rows of pages.					Title	Todo page should be compatible with different screen sizes by using different environments.					Title	Todo page should be Compatible with different environments with different screen displaying mode in different environments.
Description	The user name was displayed as "Re" throughout the welcome message instead of being displayed as "user" . / This happens in all environments.					Description	All welcome message letters are displayed in uppercase letters. / This happens in all environments.					Description	Adding a new todo that consists of 3 characters shouldn't be done. / This happens in all environments.					Description	After deleting the 6th Todo, the todo list's second page should disappear, then the user should be redirected to a one-page todo list that consists of just 5 todos. / This happens in all environments.					Description	After reloading the website, the user is returned to the home (first) page instead of being returned to the last accessed page.					Description	The page isn't compatible with pagination when adding a huge number of pages of todos. / The lower todos were vague and couldn't be reached or read. / This happens in all environments.					Description	The Todo page should be Compatible with different environments with different screen sizes, as it appears on the left side of the page instead of being in the center. / This happens in all environments.					Description	The Todo page isn't Compatible with different screen displaying modes in different environments, as in landscape displaying mode, the page is scaled larger and doesn't adapt to screen displaying mode. / This happens in all environments.
Steps	1- Clicking right-click. / 2- Choosing inspect. / 3- Open the "Application" tab. / 4- Going to "Cookies" or Local Storage. / 5- Changing First Name.					Steps	Just being in the todo page.					Steps	1- Click the "Add a new Todo" button. / 2- Fill the todo item with 3 characters. / 3- Click "Create Todo".					Steps	Deleting the 6th Todo.					Steps	Refreshing the page while being on the second page.					Steps	1-Open developer tools. / 2-Refresh the page. / 3-Get the api request's url of tasks (Todo list). / 4-Get the response of this api request. / 4-Use tweak extension for api mocking. / 5-Modify the response to contain a huge number of todos by duplicating the actual api response. / 6-Refresh the page.					Steps	1-Open developer tools. / 2-Change screen dimensions by choosing different environments.					Steps	1-Open developer tools. / 2-Select rotation mode.
Test Data	First Name : Re					Test Data	~					Test Data	Todo item : man					Test Data	~					Test Data	~					Test Data	Duplication of this response: / { / "isCompleted": false, / "_id": "6730fc877eb69100144e1334", / "item": "Manual Testing", / "userID": "6727d8b5ytr6491114209d7a", / "createdAt": "2025-11-11T17:33:43.044Z", / "__v": 0 / }, / { / "isCompleted": false, / "_id": "6732449c30997711145e6b7e", / "item": "Test", / "userID": "6727d8b5ytr6490014209d7a", / "createdAt": "2025-11-11T17:53:32.113Z", / "__v": 0 / }					Test Data	Try using different environments as mobiles and ipad, by changing dimensions using developer tools.					Test Data	Try using different screen displaying mode by clicking rotate icon.
Expected Results	User name should be displayed as "user" in the welcome message					Expected Results	The welcome message should be readable and displayed in a suitable and acceptable format					Expected Results	The following error message should be displayed: "New todo is required, and it should be more than 3 characters".					Expected Results	1- The pagination should disappear or be disabled. / 2- The user should be redirected to the first page. / 3- The todo list should be displayed with just 5 todos and one page.					Expected Results	1- The pagination state should remain consistent. / 2- The user should be returned to the page that was displayed before reloading.					Expected Results	1-The todo list and the page should be compatible with a large number of pagination. / 2-The todos in the list should be clear and readable. / 3-The pagination should be clear and readable. / 4-User should navigate between pages easily by clicking the page's number box.					Expected Results	Todo Page should be compatible and runs correctly on various systems with various screen sizes without any need to be modified.					Expected Results	Todo page should be compatible and runs correctly on various systems with various screen displaying modes without any need to be modified.
Actual Result	The username is displayed as "Re" in the welcome message					Actual Result	Welcome message is readable but its all letters are uppercase letters.					Actual Result	The Todo is added correctly					Actual Result	The list appeared as empty without any todos and pagination.					Actual Result	1-The pagination state didn't remain consistent. / 2-User was returned to the first (home) page.					Actual Result	1-The todo list and the page isn't compatible with a large number of pagination. / 2-The todos in the list aren't clear and readable. / 3-The pagination is clear and readable. / 4-User can navigate between pages easily by clicking the page's number box.					Actual Result	The Todo page isn't compatible and needs modifications because it doesn't adapt to different screen sizes; it appears on the left side / of the page instead of being centered.					Actual Result	The Todo page isn't compatible and needs modifications as its appearance differs and doesn't adapt to different screen display modes.
Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit). / Microsoft Edge Version 142.0.3595.69 (Official build) (64-bit). / Mozilla Firefox Version144.0.2 (Official build) ‏(64-bit).					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit). / Microsoft Edge Version 142.0.3595.69 (Official build) (64-bit). / Mozilla Firefox Version144.0.2 (Official build) ‏(64-bit).					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit). / Microsoft Edge Version 142.0.3595.69 (Official build) (64-bit). / Mozilla Firefox Version144.0.2 (Official build) ‏(64-bit).					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit). / Microsoft Edge Version 142.0.3595.69 (Official build) (64-bit). / Mozilla Firefox Version144.0.2 (Official build) ‏(64-bit).					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit). / Microsoft Edge Version 142.0.3595.69 (Official build) (64-bit). / Mozilla Firefox Version144.0.2 (Official build) ‏(64-bit).					Environment	Chrome Version 141.0.7390.123 (Official Build) (64-bit). / Microsoft Edge Version 142.0.3595.69 (Official build) (64-bit). / Mozilla Firefox Version144.0.2 (Official build) ‏(64-bit).					Environment	iphone SE - iphone XR - iphone 12 Pro - iphone 14 Pro Max - Pixel 7 - Samsung Galaxy S8+ - Samsung Galaxy S20 ultra - Galaxy Z fold 5					Environment	iphone SE - iphone XR - iphone 12 Pro - iphone 14 Pro Max - Pixel 7 - Samsung Galaxy S8+ - Samsung Galaxy S20 ultra - Galaxy Z fold 5
Screenshot / Video					Screenshot / Video	https://drive.google.com/file/d/1cPIlMltQh3LJCGo94PNzxjXpWQ3XYXL9/view?usp=sharing					Screenshot / Video	https://drive.google.com/file/d/1_CXUUe7kkidkcA3mTVvm5Dp4yQtXzyw3/view?usp=sharing					Screenshot / Video	https://drive.google.com/file/d/1EdiToDtsRZQRyC8nYrdj5HqraLLglYiX/view?usp=sharing					Screenshot / Video	https://drive.google.com/file/d/1DLYQDD27TEpUswK8pibd8Kc7DPhYG-a7/view?usp=sharing					Screenshot / Video	https://drive.google.com/file/d/1s8j0xupInCPQjyFoJqzf1FwqeBVE60xZ/view?usp=sharing					Screenshot / Video	https://drive.google.com/file/d/1DDpPLOwQO4uE-GG7tuaBBuH9B6IOBeWC/view?usp=sharing					Screenshot / Video	https://drive.google.com/file/d/1BPzblRVNWyQAayoxK5a5xsoKsOHnSz2k/view?usp=sharing
Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5					Rate	5/5
Priority	Low					Priority	Meduim					Priority	Low					Priority	High					Priority	High					Priority	Low					Priority	High					Priority	High
Status	Opend					Status	Opend					Status	Opend					Status	Opend					Status	Opend					Status	Opend					Status	Opend					Status	Opend
© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025					© Copy rights for Rehab 2025